## TruthLens Progress Log
Date | Learning Focus | Work Completed | Tools/Concepts
2026-02-10 | Project idea & fake news detection basics | Defined TruthLens AI goal and project scope | NLP, Fake News Detection
2026-02-11 | Python project structuring | Created repo structure and folders | Python, Git
2026-02-12 | Dataset research | Identified ISOT, LIAR, FakeNewsNet datasets | Datasets, Research
2026-02-13 | Data loading methods | Implemented dataset loading utilities | Pandas, Data Processing
2026-02-14 | Dataset merging strategies | Built merge_datasets.py | Data Integration
2026-02-15 | Data cleaning techniques | Implemented clean_data.py | Text Cleaning
2026-02-16 | Data validation concepts | Built validate_data.py | Data Validation
2026-02-17 | EDA fundamentals | Implemented EDA module and plots | Matplotlib, Analysis
2026-02-18 | Feature engineering basics | Designed feature pipeline structure | Feature Engineering
2026-02-19 | Metadata features | Implemented metadata_features.py | Feature Extraction
2026-02-20 | Source credibility features | Created source_features.py | Domain Extraction
2026-02-21 | TF-IDF understanding | Implemented text_features.py | TF-IDF, NLP
2026-02-22 | Pipeline integration | Built feature_pipeline.py | Pipeline Architecture
2026-02-23 | Transformer models overview | Studied BERT/RoBERTa architecture | Transformers
2026-02-24 | HuggingFace basics | Learned tokenizers and Trainer API | HuggingFace
2026-02-25 | Model training setup | Created train_roberta.py training pipeline | PyTorch, HF Trainer
2026-02-26 | Training experiments | Ran initial model training runs | Model Training
2026-02-27 | Evaluation metrics | Implemented evaluation module | Accuracy, F1, Precision
2026-02-28 | Visualization | Built confusion matrix visualization | Visualization
2026-03-01 | Cross validation concepts | Implemented cross_validation.py | Model Validation
2026-03-02 | Hyperparameter tuning | Implemented Optuna tuning module | Optuna
2026-03-03 | Model saving/loading | Built model_utils.py | Serialization
2026-03-04 | Prediction pipeline | Implemented predict.py inference logic | Inference Pipeline
2026-03-05 | API fundamentals | Learned FastAPI basics | FastAPI
2026-03-06 | API implementation | Built api/app.py endpoints | REST API
2026-03-07 | Model serving flow | Integrated model inference with API | Model Serving
2026-03-08 | Configuration management | Built config.yaml + settings loader | Config Management
2026-03-09 | Logging and utilities | Added logging utilities and helpers | Logging
2026-03-10 | Testing basics | Created initial unit tests | Pytest